## Page_2
|  | prevent others from voting from my account | make sure the
2.Agile User Story Template
Version: 1.0 |  |  | Date: 07-10-2018
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | Voter | Login with an ID | keep my account safe
2 | Voter | Vote | participate in the election
3 | Voter | Use blockchain to prevent others voting from my account | prevent fraudulent votes
4 | Voter | View the votes secured by each candidate at the end of the election | verify the results myself
5 | Admin panel | Register Voters | set the elligible voters
6 | Admin panel | Compute and publish the result at the end | let every voter view it
Approval by Guide

## Page_3
3. PRODUCT BACKLOG
*To be planned before sprint starts
Version: 1.0 | [6 empty] | Date: 06-09-208
User Story ID | Priority <High/Medium/low> | Story Points | Size (Hours) | Total | Sprint <#> | Status <Planned/In progress/done> | Release Date | Release Goal
1 | Medium | 6 | 4 | 4 | 1 | Planned | 2018-09-11 | User Interface will be created
5 | High | 7 | 6 | 12 | 1 | Planned | 2018-09-17 | Users will be registered
1 | High | 8 | 6 | 16 | 1 | Planned | 2018-09-24 | Users will be able to login
2 | High | 10 | 7 | 22 | 2 | Planned | 2018-10-01 | Users will be able to vote
3 | High | 9 | 8 | 30 | 2 | Planned | 2018-10-08 | Ensure single vote per voter
6 | High | 7 | 7 | 37 | 3 | Planned | 2018-10-15 | Results will be computed and added to the blockchain
4 | Medium | 5 | 6 | 43 | 3 | Planned | 2018-10-22 | Users will be able to view the result
* Story points out of 10 may be assigned based on priority
|  |  | Approval by Product owner |  |  |  | Approval by Guide

## Page_4
4.Agile Project Plan
*To be planned before sprint starts
| Version: 1.0 |  |  |  | Date: 06-10-2018
Overall Progress: 5%
User Story ID | Task Name | Responsible | Start date | End date | Days | Status (to be filled by Scrum Master)
| Sprint 1 | Nandakishore VV | 2018-09-10 | 2018-09-24 | 14
1 | Create Interface | Nandakishore VV | 2018-09-10 | 2018-09-11 | 2
5 | Register Users | Nandakishore VV | 2018-09-11 | 2018-09-17 | 6
1 | User Login | Nandakishore VV | 2018-09-18 | 2018-09-24 | 6
| Sprint 2 | Nandakishore VV |  |  | 0 | Not Started
| Task 4 | Nandakishore VV |  |  | 0 | Not Started
| Task 5 | Nandakishore VV |  |  | 0 | Not started
| Task 6 | Nandakishore VV |  |  | 0 | Not started
Approval by Scrum Master

## Page_5
5.SPRINT BACKLOG (PLANNING)
*To be planned before sprint starts
Sprint: # | [11 empty] | Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:
Backlog Item | Story Points | Responsible | Status and Completion date | Original Estimate in hours | Day 1 <Date> | Day 2 <Date> | Day 3 <Date> | Day 4 <Date> | Day 5 <Date> | Day 6 <Date> | Day 7 <Date> | Day 8 <Date>
User Story #1 | 8 |  |  |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
<Task > |  | <Developer Name> | Planned, 12/09/2018 | 2 | 1 | 1 | 0 | 0 |  |  |  | 0
Task |  |  |  | 4 | 2 | 0 | 2 | 0 |  |  |  | 1
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 |  |  |  | 0
Task |  |  |  | 1 | 1 | 2 | 3 | 1 |  |  |  | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  |  |  | 0
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  |  |  | 1
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  |  |  | 0
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  |  |  | 0
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  |  |  | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  |  |  | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  |  |  | 1
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  |  |  | 0
User Story #4 | 8
Total |  |  |  | 35.5 | 28 | 26 | 18 | 8 |  |  |  | 3
Remaining Story Points:
Signature of Scrum Master

## Page_6
6. SPRINT BACKLOG (ACTUAL)
*To be filed at the end of each sprint
Sprint: # | [11 empty] | Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:
Backlog Item | Story Points | Responsible | Status and Completion date | Original Estimate in hours | Day 1 <Date> | Day 2 <Date> | Day 3 <Date> | Day 4 <Date> | Day 5 <Date> | Day 6 <Date> | Day 7 <Date> | Day 8 <Date> | Done <Y/N> to be filled by Scrum Master
User Story #1 | 8 |  |  |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
<Task > |  | <Developer Name> | Completed, 12/09/2018 | 2 | 1 | 1 | 0 | 0 |  |  |  | 0 | Y
Task |  |  |  | 4 | 2 | 0 | 2 | 0 |  |  |  | 1 | N
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 |  |  |  | 0 | N
Task |  |  |  | 1 | 1 | 2 | 3 | 1 |  |  |  | 0 | N
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  |  |  | 0
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  |  |  | 1
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  |  |  | 0
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  |  |  | 0
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  |  |  | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  |  |  | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  |  |  | 1
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  |  |  | 0
User Story #4 | 8
Total |  |  |  | 35.5 | 28 | 26 | 18 | 8 |  |  |  | 3
Remaining Story Points:
Signature of Scrum Master

## Page_7
7. Database & UI Design
*To be planned before sprint starts
Sprint <#>
Version No.
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
<Include Database design and User interface design >

## Page_8
8. Testing and Validation
Version: 1.0 |  | Sprint#: 1
Test # | Date | Action | Expected Results | Actual Results | Pass? <Yes/No>
1 | 2016-03-06 | Logging in | Should get to home screen | User directed to different page | Yes
2 | 2016-03-12 | Signing up for webinar | Get confirmation email | Confirmation email received | No
3 | 2016-03-20 | Click magnifying glass | Whole page gets bigger | Text changes sizes | Yes
4 | 2016-04-01 | Click blog post hero image | Go to blog post | Go to blog post
Approval by Scrum Master